## CD Transformation Checkpoints and Metrics
	CD Transformation Checkpoints and Metrics
Each code submission triggers the pipeline in serial
Jenkins provides CI pipeline
CI pipeline is fully automated
Single source repository/trunk
All artifacts kept in version control
All Commit Phase failures stop the pipeline
SPRs add data to track test escapes
Push-button automated pre-submission validation
All new code is code reviewed
All new code has unit and functional test coverage
Automated tests added for all resolved SPRs
All test deployments use production deployment processes and are fully automated/repeatable
All test deployments use production-congruent environments/stacks
Full regression/compatibility testing of APIs and extensions
Simian Army testing occurs continuously
Dashboard metrics gathering is automated
Continuous on-premises testing (NFR and on-prem only features)
Zero downtime updates

## Transformation Metrics
Phase	Metric	Measurement Value
Commit Phase	Build Duration	Minutes
	Commit Phase Testing duration (automated)	Person Weeks	would be nice to have – include 1 team
Acceptance Test Phase	API Test Coverage (via automated measurement)	% Value	dropped
Manual Test Phase	Manual testing duration (non-automatable)	Person Weeks	not applicable in a CD world
	Time from final code submission to production (Cloud)	Days	Dropped – not a priority
	Time from final code submission to GA (On-Premises)	Days	Dropped – not a priority
	SPRs opened per capita (general quality measure)	Number
CD Business Value	Cumulative open+deferred defects (technical debt)	Number

Customizable Project Selection – Metrics

Issues
Build Duration : Graphing Defect – not renderng properly at a top level – looks OK on the lower level. Mitigation – link to graph from top page – not blocking

week of 31st - 1.5 days
week of 7th - 1.5 days
week of 14th - 3 days
week of 21st - 3 days

23rd - 95% finished

9 working days between now and the end of the project