Shane Murphy	Overall Status
ITT – ICS CD Adoption Dashboard	Green
ITT – ICS CD Adoption Dashboard
Milestone	Target Date	Actual Date	Status
Use cases and Technical Architecture	28/10/ 2013	22/10/2013	Complete
Prototype 1	11/12/ / 2013	11/12/ / 2013	Complete
Prototype 2 – Exam Break	10/01/ / 2014	10/01/2014	Complete
Restart Dev	03/02 / 2014	03/02/2014	Complete
Easter Break	14/04 / 2014
Complete	07/05/ / 2014
Demo and Handover	12/05 / 2014
Accomplishments:
Added refresh page functionality
Grouped defects into s1, s2 and s3 levels.
Separated build time and test time into two separate charts
Fixed image linking issues
Implemented Cron Job methods to update domain when RTC server changes*
While implementing these methods, was having NPE problems, made all code Null safe.
General Refactoring
Installed DB2.
Upcoming Work:
Add WorkItem State
Switch to DB2 database
Issues/risks:
Trial License expired 12 April. Cannot create WorkItems under Builds/Projects. Can create Project, which demonstrates the update methods working. Domain is updated in background.
Cannot find a way to automatically refresh the page when domain is updated because the Cron Job has no user session associated with it. Added refresh button instead.
Trouble installing DB2, took a long time, now trying to create database and swap over.