	Overall Status
ICS CD Adoption Dashboard	Green
ITT - ICS Continuous Delivery Adoption Dashboard
Milestone	Target Date	Actual Date	Status
Use cases and Technical Architecture	28/10/ 2013	22/10/2013	In progress
Prototype V 1	11/13/ / 2013
Prototype V 2	12/11/ / 2013
Accomplishments:
Tech Research and Comparison
Installed environment software
User Stories
Upcoming Work:
Review User stories With Mentor
Format tech research into tech architecture document and research document.
Issues/risks:

---
ICS CD Adoption Dashboard	Green
ITT - ICS Continuous Delivery Adoption Dashboard
Use cases and Technical Architecture	28/10/ 2013	22/10/2013	Completed
Completed Use Cases
Decided on Technologies to be implemented
Learning Groovy/Grails basics (Tutorials)
Set up IDE environment
Looking at IBM OneUI files and documentation
Class Diagrams
Logical Architecture Diagram
Use OneUI files to create View Templates in grails
Create Model classes based on Class Diagrams

---
Shane Murphy	Overall Status
ITT – ICS CD Adoption Dashboard	Yellow
ITT – ICS CD Adoption Dashboard
Use cases and Technical Architecture	28/10/ 2013	22/10/2013
Installed JTS, RTC, RM, CCM and QM Server.
Identified and installed Sample Project (JKE Banking)
Making progress towards an app GUI template while slowed down in other areas
IBM OneUI CSS linked in, but not being applied to the web app, unsure why, need to rectify this.
Little work done on actual code due to roadblocks/slow downs, need to get some responses from the server to display for the prototype.
JTS etc. requires a large amount of RAM, More than I have available, more has been ordered but am waiting for it to arrive.
In the meantime I have set up the server on a desktop which can be accessed from my local home network.
When Installing JKE Banking sample I always encounter an error, I'm not sure what is missing, but it seems like what has installed should be enough for what I need.

---
ITT - <project name>	<status colour>
ITT - <project name>

---
ITT - <project name>	<status colour>
ITT - <project name>