Shane Murphy	Overall Status
ITT – ICS CD Adoption Dashboard	Green
ITT – ICS CD Adoption Dashboard
Milestone	Target Date	Actual Date	Status
Use cases and Technical Architecture	28/10/ 2013	22/10/2013	Complete
Prototype 1	11/12/ / 2013	11/12/ / 2013	Complete
Prototype 2 – Exam Break	10/01/ / 2014	10/01/2014	Complete
Restart Dev	03/02 / 2014	03/02/2014	Complete
Easter Break	14/04 / 2014
Complete	07/05/ / 2014
Demo and Handover	12/05 / 2014
Accomplishments:
Project rescoped to a Commit Phase Dashboard
Added user login and added associated profile
User can now select which teams to show/hide
Bootstrapped sample data – Still retrieves from RTC as well.
Added About page
Displaying defects grouped by severity (pie chart)
Displaying build time, average build time and commit phase testing time on a line graph.
Upcoming Work:
Workitem state grouping (Issue)
Implement existing stub methods to update local database. (i.e. only update entities that have an update available)
Auto refresh page periodically
Issues/risks:
Used to be a WorkItem State property, this has been replaced with a state2 property which doesn't include the field I need to group workItems into Open/Deferred states.