Shane Murphy	Overall Status
ITT - ICS CD Adoption Dashboard	Green
ITT - ICS Continuous Delivery Adoption Dashboard
Milestone	Target Date	Actual Date	Status
Use cases and Technical Architecture	28/10/ 2013	22/10/2013	In progress
Prototype V 1	11/13/ / 2013
Prototype V 2	12/11/ / 2013
Accomplishments:
Tech Research and Comparison
Installed environment software
User Stories
Upcoming Work:
Review User stories With Mentor
Format tech research into tech architecture document and research document.
Issues/risks:

---
ITT - ICS CD Adoption Dashboard	Green
ITT - ICS Continuous Delivery Adoption Dashboard
Use cases and Technical Architecture	28/10/ 2013	22/10/2013	Completed
Completed Use Cases
Decided on Technologies to be implemented
Learning Groovy/Grails basics (Tutorials)
Set up IDE environment
Looking at IBM OneUI files and documentation
Class Diagrams
Logical Architecture Diagram
Use OneUI files to create View Templates in grails
Create Model classes based on Class Diagrams

---
ITT – ICS CD Adoption Dashboard	Green
ITT – ICS CD Adoption Dashboard
Use cases and Technical Architecture	28/10/ 2013	22/10/2013
Installed extra RAM
After additional research, switched from REST API to Java API
Identified where to find information needed for summary statistics in RTC (Build Duration, SPRs, Defects).
Created RTC Service which can access projects (Teams) and all builds under these projects. Access to members of each team also provided.
Updates to class diagrams as more information obtained from returns in the code.
Updated models to hold information that may be relevant where more granularity may be of use.
Access Work Items for each project (For Defects and SPRs).
Database setup methods. (Retrieve all information and store it as a starting context to be later updated by other methods)
Asses how to access information in RQM.
OneUi CSS is not being applied to HTML for some reason.

---
Use cases and Technical Architecture	28/10/ 2013	22/10/2013	Complete
Prototype 1	11/12/ / 2013	11/12/ / 2013	Complete
Prototype 2 – Exam Break	10/01/ / 2014
Restart Dev	03/02 / 2014
Easter Break	14/04 / 2014
Complete	07/05/ / 2014
Demo and Handover	12/05 / 2014
Installed extra RAM
After additional research, switched from REST API to Java API
Identified where to find information needed for summary statistics in RTC (Build Duration, SPRs, Defects).
Created RTC Service which can access projects (Teams) and all builds under these projects. Access to members of each team also provided.
Updates to class diagrams as more information obtained from returns in the code.
Updated models to hold information that may be relevant where more granularity may be of use.
Access Work Items for each project (For Defects and SPRs).
Database setup methods. (Retrieve all information and store it as a starting context to be later updated by other methods)
Asses how to access information in RQM.

---
Use cases and Technical Architecture	28/10/ 2013	22/10/2013	Complete
Prototype 1	11/12/ / 2013	11/12/ / 2013	Complete
Prototype 2 – Exam Break	10/01/ / 2014
Restart Dev	03/02 / 2014
Easter Break	14/04 / 2014
Complete	07/05/ / 2014
Demo and Handover	12/05 / 2014
Time spent understanding REST – better use of time to return to RTC and Java API to finish functionality here before tackling RQM/Jenkins functionality
Split Services out into DomainService and RTC Service
Domain classes aded and cardinality constraints implemented and cascade delete operations – Key constraint issues originally.
Method to retrieve database state fully functional for Teams and Builds.
Average Build Time for team passed into teamInfo view.
Views implemented for Teams/Builds/WorkItems.
Fix WorkItems issues.
Implement graphic representation for build times (over time).
Debug CSS issues.
Breakpoints do nothing.
Intermittent issues with Domain methods (get() exists())
WorkItems not saving or associating with their builds, but are being retrieved correctly from the server.
WorkItems proving to be difficult – Issues saving them, got this working, then constraint (many to many) issues when deleting (dropping entire tables for testing), fixed this and workitems were no longer saving